## 1. Decisions (locked)
# | Decision | Locked answer | Owner | Confirm on next call?
1 | Product & use case | InvestigateIQ — AI-Powered AML Investigation Copilot. Frozen scenario: rapid movement of funds, Apex Global Trading Ltd. Twin case: C1 suspicious / C2 legitimate. | Sweta Singh | Just ratify — everything else already built on this
2 | Interaction model | Copilot (single workspace + natural-language chat), not a multi-screen product. See CEO Playbook Sec 1.3. | Sweta Singh | No
3 | Jurisdiction / context | India, illustrative only — no specific regulation cited without a compliance-literate reviewer's check. | Lakshmi | No
4 | Submission track | Blueprint + shallow prototype. | Sweta Singh | No
5 | Who presents (15 min incl. Q&A) | Sweta Singh (proposed) — backup: Soumya | Sweta Singh | YES — confirm or swap
6 | Who owns final integration/QA of the document | Sweta Singh | Sweta Singh | No
7 | Architecture / tech stack | Streamlit + SQLite, RAG over OKF knowledge base, single orchestrating AI agent (5 logical agent roles). See CEO Playbook Sec 4-6. | Rahul Chainani | No
8 | Repo & deployment | GitHub: swetadminc/CapstoneProject. Railway: auto-deploys on every push to main, DB rebuilds on every deploy. | Rahul Chainani | No — already live
9 | LLM provider & API key/budget | OPEN — not yet chosen. Needed before AI agents can be wired to a real model. | Rahul Chainani + Pankaj | YES — must decide this week
10 | Next check-in | Daily 15-min stand-up until submission. | Sweta Singh | YES — pick a time

## 2. Roles & responsibilities
Role | Person (proposed — swap freely) | Responsibility | Where it's documented | Status
CEO / Product Visionary | Sweta Singh | Freeze scope, approve guardrail language, own demo narrative, present. | CEO Playbook Sec 1, 8.1, 11 | In progress
Solution Architect | Rahul Chainani | Architecture, tech stack, data/tool layer, agent orchestration, Grounding Validator, Railway/infra. | CEO Playbook Sec 4, 6; this repo's app.py / data/ | In progress — DB + deploy live
Business Analyst | Lakshmi | Requirements & acceptance criteria, C1/C2 data spec, playbook/policy entries (the OKF knowledge-base content). | CEO Playbook Sec 6, 9; Product Docs/dataset/knowledge_base/ | Not started
UI / UX | Laxman Singh | Build the 3-panel Streamlit workspace from the wireframe; evidence tags; accessibility & projector pass. | CEO Playbook Sec 7 | Not started — placeholder app live, real workspace not built
AI/ML + Backend Engineer (lead) | Pankaj | Context/Discovery/Evidence/Conclusion agents, RAG retrieval, LLM integration. | CEO Playbook Sec 5, 6 | Not started — blocked on LLM API key (Decision #9)
AI/ML + Backend Engineer (support) | RS | Pairs with Pankaj; owns test scenarios (missing/conflicting/prompt-injection cases) and cached-report fallback. | CEO Playbook Sec 11 test scenarios | Not started
QA & Presenter (backup) | Soumya | Demo script rehearsal, timing, backup presenter, final run-throughs. | CEO Playbook Sec 11 | Not started
This is Claude's first-cut assignment based on the only real signal available (Rahul = group admin, Sweta has driven direction) — not a claim about anyone's actual skills. Swap names in under 2 minutes on the call; the roles and responsibilities themselves are the part that's actually decided.

## 3. Team & strengths
Member | Strengths / background | Available hours/week | Proposed role | Confirmed?
Sweta Singh |  |  | CEO / Product Visionary
Rahul Chainani |  |  | Solution Architect
Lakshmi |  |  | Business Analyst
Laxman Singh |  |  | UI / UX
Pankaj |  |  | AI/ML + Backend Engineer
RS |  |  | QA & Presenter (backup)

## 4. Timeline
Date | Milestone | Owner | Status
Day 1 — 28 Sep (today) | Use case/scope frozen. Architecture confirmed. GitHub live. Railway deployed with DB + placeholder app. | Sweta, Rahul | DONE
Day 2-3 — 29-30 Sep | Mock data (C1/C2) finalized [done]. OKF knowledge-base docs authored [done, 10 docs]. 3-panel workspace scaffolded. | Lakshmi, Laxman | Data/KB done; workspace UI not started
Day 4-5 — 1-2 Oct | Context+Discovery agents built. Evidence+Conclusion agents + Grounding Validator built. RAG wired in. Evidence tags + chat UI wired. | Pankaj, RS, Laxman | Not started — needs LLM API key
Day 6 — 3 Oct | Integration + bug fixes. Demo reports cached. Accessibility/projector pass. First full timed run-through. | Whole team | Not started
Day 7 / Submission — 4-6 Oct (adjust to real date) | Second timed run-through. Live/cached toggle verified. Final sign-off. Present. | Whole team, Sweta | Not started
1st-2nd week Oct | SUBMISSION WINDOW — confirm exact date/portal from the email. | Sweta | Open